**FUNDAMENTALS OF BUSINESS ANALYSIS**

**Group project Brainstorming**

**Mark Gaskin**

**Keith Redmond**

**Patrick Moran**

**Scrum 1:**

**19th October 18:00 - 18:24**

**In class discussion**

**Mark, Patrick and Keith discussed the elicitation techniques that will be used.**

**Based on the discussion and on the weight of work to be done the below techniques were selected:**

* **Brainstorming**
* **Prototyping**
* **Observation**
* **Survey**

**Tasks:**

**For Saturday 21st October each person was tasked with briefly outlining what each technique would require, how it should be structured and what the outcome should provide.**

**Scrum 2:**

**22nd October 18:57 – 20:45**

**What’s App group Discussion**

**The group discussed the outcome of the elicitation techniques outline completed on the 21st October.**

**Each member set out what they believe to be the pressure points for each elicitation technique. This outline is now open to be incorporated into the main process.**

**The team also designed the structure of the main requirements document. All documents and outlines have been saved to the Github repository.**

**Scrum 3:**

**30th October 18:14 – 19:45**

**What’s App Group Discussion**

**Discussion held around starting of the observation technique. Patrick confirmed that he has completed the first non-student website observation. Keith and Mark to organise further observations.**

**Scrum 4:**

**6th November 14:40 – 21:30**

**What’s App Group Discussion**

**The team discussed all questions to be included on the survey monkey survey site. Several questions were mentioned with 10 of the best selected. Once the questions were confirmed the survey was formatted and the sent to class mates to complete.**

**An email was sent to NCI management requesting access to all students email’s so that a mass email can be sent with our survey. Awaiting reply.**